St Nicholas CIW Primary School

School Development Plan Summary

2025-2026

The school’s vision

Our Spiritual Core = FAMILY

“Faith + Family + Future = Endless Possibilities”

Spiritual Vision

A school family that lives according to the teachings of Christ and its Christian values. Each member of the school family is valued and loved as a unique child of God.

We therefore aim to be a

Family of capable learners who are independent, respectful and empathetic members of society who are ready to develop a broad range of knowledge and skills within a digital world. (Respect)

Who are

Able to engage and communicate effectively as a member of their own culture, community, Wales and the wider world. (Friendship)

Who

Manage risks, rise to challenge and set high expectations of themselves and others. You will engage with contemporary issues and show commitment to the sustainability of our planet.  (Hope)

Which

Ignites creativity and grasps opportunities to be enterprising contributors ready to play a full part in life and work. (Courage)

Whom

Live a full and healthy life through building physical and mental resilience. You will understand the impact of your actions and behaviours as you grow and develop. (Forgiveness)

Finally

You will be part of our democratic school and will be valued and loved as an individual as part of our Christian Family. (Love)

*Core values of our school

| St Nicholas CIW Primary Development Plan Priorities 2025 - 2026 |  |  |
| --- | --- | --- |
| IA1 – Teaching & Learning / Curriculum |  |  |
| - Refine the methods used to capture and track pupil progress to ensure accurate and actionable data. - Enhance the reading culture and develop pupils’ comprehension skills across all year groups. - Innovate writing pedagogy to improve pupils’ engagement and writing outcomes. - Improve provision for More Able and Talented (MAT) pupils to ensure they are appropriately challenged. |  |  |
| Rationale Rationale 1a Pupil Progress • Snapshots have been developed in PE and DT. This approach will be developed across other AOLES as it is an effective approach to capture ongoing progress • Current baseline does not support ongoing assessment procedures across the school and therefore does not provide an ongoing progress model that supports pupil development • As a self-improving school we are always continuing to strive to improve how we assess pupils and capture progress. 1b – Writing • Following on from work completed in Oracy, a disconnect between writing and Oracy rehearsal methodology has been identified. • Not all writing schemes in PS2 and PS3 follow the Oracy rehearsal model in PS1. • Comparative judgements have identified punctuation and grammar as areas in need of development. • Progressive approaches to the teaching of the 6 non-fiction text types has been identified as an area in of need of further refinement. • To build on the progress of Welsh oracy writing has been identified as the next area of focus. 1c - Reading • National testing demonstrates inconsistencies in progress with reading comprehension. 39.6% of the current year 4- 6 did not maintain or make progress 46% of eFSM (6 pupils ) • LA priority to strengthen and improve progress in reading. • It has been identified that the overuse of digital materials has affected the stamina of reading and a love of real books. • Monitoring has demonstrated inconsistencies in approaches to Guided Reading. • Reading areas need further development to make them more enticing and engaging. 1d – Assessment in Maths • Align assessment procedures with the newly adopted curriculum – review and update existing assessment systems to ensure they accurately reflect and support the content and skills of the new curriculum. • Increase awareness and use of class snapshots – ensure leaders and staff understand, contribute to, and effectively use class snapshot data to inform teaching, track progress, and identify targeted support. • Monitoring shows inconsistencies in approaches to formative assessment including how cold/hot assessments are generated, administered and used to accelerate progress. • Monitoring shows inconsistencies in the regularity of using Can Can’t Could Assessments formatively 1e - To further enhance opportunities for MAT • A minority of more able pupils are not consistently stretched in their learning. • Limited Opportunities were given pupils to explain, and act as experts. • Currently talent is celebrated in the school however further opportunities to develop a legacy of talent to inspire future generations needs to be developed. |  |  |
| Autumn Milestones | Spring Milestones | Summer Milestones |
| 1a •PE and DT snapshots have been shared and embed in practice and comparative data snapshots in writing have been established. •Baseline has been reviewed and amended to ensure progress can be measured effectively •Pupil progress meetings have been held •Class on a page have been established in all classes 1b • Writing comparative judgements have been made and areas of improvement have been identified. • Areas in need of improvement will have been developed in teaching and learning. • Learning walks will demonstrate consistency in talk for write strategies in PS1 and that PS2 and PS3 have implemented initial PC talk for write units of work. • Non-Fiction approach has been reviewed and amended. • Poetry spine has been disseminated to staff. • Staff meeting has been held looking at Welsh medium term planning. • Staff have made amendments to planning in order for them to improve links with topics. • Welsh writing genres are mapped out for the year. • Each class has produced two pieces of Welsh writing by the end of term linked to either, Welsh units, topic or calendar events. • Welsh writing has been monitored by the end of term. 1c • Staff will have analysed data in conjunction with knowledge passed on by previous staff and initial judgements to identify learners that would benefit from intervention support at Waves 1&2 of the ALN routemap. Intervention support has been put in place for identified learners. • Structure for skills led Guided Reading approaches has been shared with all staff. • Listening to learners baseline regarding reading culture has been carried out. • Reading culture hymn sheet has been co-constructed with staff. • Reading initiative has been established across the school to promote reading both at home and in school. • Reading ambassadors have been established. • Each classroom has developed reading areas and made them more inviting. 1d • All teachers audit current practise to identify strengths and areas for development. • All teachers understand the role of cold/hot tasks in diagnosing gaps and measuring progress and that assessment is linked to responsive teaching. • All teachers take ownership of assessment design; more personalised pupil assessments observed based on year group expectations. • Older pupils begin to describe the purpose of cold/hot tasks and can talk about progress simply • Emerging evidence of responsive planning based on cold task outcomes. Teaching focuses on identified high-impact gaps to plan sequences of learning. • Teachers begin to track progress using hot/cold assessment snapshots • LSAs leading intervention liaise weekly with teachers to identify targeted skills that have not yet been mastered by 20% of the cohort. 1e • Following data analysis, MAT pupils have been identified for focused challenge and extension. • Work scrutiny and pupil questionnaires have been carried out and demonstrate that some pupils identified as MAT are being challenged and extended in their learning. • Peer mentor coaching has been established in PS3. • Area on website to celebrate pupils’ talents has been established. • Area in hall to celebrate achievements of talented pupils has been established. | 1a • Art, music and dance snapshot templates have been shared with staff and are being used effectively. • Pupil progress meetings have been held. 1b • Comparative judgment process has been repeated using a cold piece of non-fiction writing and data demonstrates progress has been made in identified areas. • Agreed Non-Fiction amendments have been put in place. • Each class has produced two pieces of Welsh writing by the end of term linked to either, Welsh units, topic or calendar events. • Welsh writing has been monitored by the end of term. 1c • Data analysis demonstrates that most pupils identified as needing additional support have continued to close the attainment gap. • WAG reading tests have been re-taken and data analysis demonstrates that most pupils have maintained or improved standardised scores. • Learning walks demonstrate that new Guided Reading approaches are being implemented. • Learning walks demonstrate that staff are adhering to the reading culture hymn sheet, with all initiative being put in place and reading corners being more inviting with books being changed more regularly. 1d • Mid-point review has taken place. All teachers reflect critically on practice and identify immediate refinements. Immediate coaching where gaps are identified. • Half termly reviews show All teachers have implemented unit (conker) hot/cold progress assessment snapshots (80% cohort mastery tracking) identifying learners for intervention fluidly. • Most pupils (Y3-6) begin to talk confidently about their targets in maths and can talk about how they measure their improvements in their learning • Higher quality cold and hot tasks designed in-house by teachers. • Most teachers report greater confidence in assessing age expected standards, identifying the stage of all learners leading to better progress for all pupils. • Learning journeys reflect agreed changes to assessment design. • Trackers are updated at the start and at the end of each unit of work. • LSAs develop confidence in independently identifying gaps in learning so that they make good progress from their starting points. 1E • Following data analysis, MAT pupils have been identified for focused challenge and extension. | 1a • All snapshot templates have been shared with staff and are being used effectively to capture progress. • YR1 progress has been measured more effectively against Baseline. • Pupil progress meetings have been held to review the progress of all learners over the year. 1b • Comparative writing task will be repeated in readiness for analysis in the Autumn Term. • Learning walks will demonstrate a consistency in implementation of PC talk for write strategies in PS2 and PS3. • Book scrutiny demonstrates that agreed Non-Fiction amendments are being used consistently across all PS’s. • Listening to learners and book scrutiny demonstrates that standards in the 3 strands of poetry are improving. • Each class has produced two pieces of Welsh writing by the end of term linked to either, Welsh units, topic or calendar events. • Welsh writing has been monitored by the end of term. 1c • Pupil progress meetings have been carried out and data demonstrates that pupils receiving intervention support for reading have continued to close the attainment gap. •WAG reading test data demonstrates that most pupils have continued to make good progress and fewer than 25% of standardised scores have fallen. • Listening to learners feedback on reading culture shows an increased positive attitude towards reading. 1d •End of project review shows all teachers have confidently embedded assessment snapshots into their practise. • Half termly reviews show all teachers have continued to implemented unit (conker) hot/cold progress assessment snapshots (80% cohort mastery tracking) identifying learners for intervention fluidly. • Nearly all pupils (Y1-6) will demonstrate improved understanding of how they have made progress at the age-appropriate level. • High quality cold and hot tasks designed in-house by teachers. • Standards in maths improve; the attainment gap narrows, especially for vulnerable learners. • Learning journeys reflect changes implemented. • Whole school picture of pupil performance in maths has been generated and shared with staff in preparation for next year • LSAs confidently run interventions to support the 20% that have not secured mastery at the year group expectation. 1e • Following data analysis, MAT pupils have been identified for focused challenge and extension. • Work scrutiny and pupil questionnaires have been carried out and demonstrate that nearly all pupils identified as MAT are being challenged and extended in their learning. • Learning walk demonstrates that peer mentor coaching has enabled pupils to articulate their thinking. |

| St Nicholas CIW Primary Development Plan Priorities 2025 - 2026 |  |  |
| --- | --- | --- |
| IA2 – Whole School Development / Wellbeing & Inclusion |  |  |
| - Improve overall pupil attendance to meet or exceed national expectations. - Implement the ALN Act effectively to support pupils with additional learning needs. - Strengthen pupil voice through structured opportunities for input and feedback |  |  |
| Rationale 2a and 2b ALN • The ALN bill is fully implemented, but a consistency in approach to supporting vulnerable learners without an IDP needs to be developed. 2c Bullying • SHRN data demonstrates that in St Nicholas the percentage of pupils that perceive themselves to be bullied in current YR4 & YR5 is 6% higher than the Wales average. (However, the school percentage for years 3-6 last year is lower than the Wales average.) • The SPECTRUM VAWDAS Project is a Wales wide initiative to tackle Violence Against Women, Domestic Abuse and Sexual Violence in both Primary and Secondary Schools. 2d Physical Activity and Outdoor Learning • SHRN data states that the number of pupils in years 3-6 (last year) that exercise at least 5 times a week is 5 % lower than the Wales average. • SHRN data states that the percentage of pupils that own smart devices are higher than the Wales average (9% higher for smart phones and 2% higher for other devices). • SHRN data states that the percentage of pupils that use devices for various activities either daily or a few times a week is higher than the Wales average (3% higher for watching videos, TV or playing computer games, 20% higher for speaking to family and friends and 11% higher for using social media and apps. 2e Pupil Voice • SHRN data for YR5&6 (last year) states that 6% fewer pupils agree or strongly agree that they have a say in planning school activities and 1% fewer agree or strongly agree that they have a chance to help plan school projects. 2f Attendance • Attendance continues to be a nationwide priority and is not recovering from pre-covid levels. • 23/24 - 92.76 % efsm 91.4% 24/25- 93.3% efsm- 92.13 % Wales average = 90.9% Vale of Glamorgan = 91.2% |  |  |
| Autumn Milestones | Spring Milestones | Summer Milestones |
| 2a – Supporting Vulnerable Pupils - Route maps for ALN identification and provision have been established and actioned. - Half termly surgeries have been held between ALNCo and class teachers to ensure that provision is in line with the route map and remains appropriate. - Support plans (previously Class Based Target Profiles) for pupils receiving universal provision have been refined to maximise effectiveness in targeting and monitoring provision and progress. - All class teachers have set up individual support plans for all pupils receiving wave 2 provision as recorded on the ALN route map. - Support plans and pupil progress has been reviewed and provision tailored and tweaked to ensure it remains appropriate to need. - Dyslexia screening program has been used to assess all YR3 pupils as well as any other pupils with specific learning difficulty concerns, and used to provide appropriate provision for pupils identified with specific needs. - An ELSA and wellbeing route map and robust referral system has been developed and used to ensure support is targeted and appropriate to need. - ELSA and wellbeing termly review has been held between ELSA trained staff and ALNCo to plan for support for Spring Term. - Timing and costs of ELSA training have been sought and plans made for another member of staff to be trained. 2b – Outside Agency Support - ALNCo has met with outside agencies and has a better understanding of entry and exit criteria and referral processes for a wider range of outreach services. - ALNCO has attended two ALNCo days and made enquiries as to any other outreach services that are available. - ALNCo has signposted staff to outreach services for pupils discussed during ALN surgeries where appropriate to do so. 2c - Bullying - Hold a parent workshop to raise awareness of what constitutes bullying, school procedures, and support available. - Continue use of check-in cards across the school, ensuring all pupils know how to use them to share concerns at least twice a day - Begin targeted bullying workshops for identified year groups. - Join the Voices Against Bullying Programme and embed key messages into assemblies and class discussions. 2d – Health & Wellbeing - 10-minute daily activity timetabled by AOLE coordinator and launched in all classes. - Hall display created to showcase and track active participation across the school. - Healthy Schools Committee ensures active play is timetabled and equipment is accessible during break/lunch. - At least one after-school sports club reinstate 2e – Pupil Voice - School Senedd revisits roles and expectations, ensuring each group (Healthy Schools, Eco, Criw Cymraeg, School Council) sets its own priorities and targets. - First Minister and Deputy begin to hold groups to account by reviewing progress at Senedd meetings. - Global Gang is formally established with clear objectives and links to equity, diversity, and international/global learning. - Begin trialling learning pit stops within immersion days to gather pupil feedback on activities and learning 2f - Attendance - Weekly: Class with highest attendance wins the “Attendance Cup” and extra playtime. - Every Day Counts Fortnight: Pupils with 100% attendance over the two weeks entered into a prize draw (e.g. books, toys, vouchers). - Half Term: Pupils with 100% attendance entered into a lucky dip prize draw. - End of Term: Certificates and bronze attendance badges awarded to all pupils with 100% attendance. “Most Improved Attender” recognised in assembly. | 2a – Supporting Vulnerable Pupils - Half termly surgeries have been held between ALNCo and class teachers to ensure that provision is in line with the routemap and remains appropriate. - Support plans and pupil progress has been reviewed and provision tailored and tweaked to ensure it remains appropriate to need. - Dyslexia screening has been repeated with all pupils identified as needing additional support to monitor progress and plan next steps in intervention. - ELSA and wellbeing termly review has been held between ELSA trained staff and ALNCo to plan for support for Summer Term. - ELSA training has taken place/is booked. 2b – Outside Agency Support - ALNCo has signposted staff to outreach services for pupils discussed during ALN surgeries where appropriate to do so. 2c - Bullying - Monitor and evaluate the use of check-in cards, reviewing logs and pupil feedback on their effectiveness. - Repeat the SHRN questionnaire to capture pupils’ perceptions of bullying and compare with previous responses. - Extend pupil discussions (through Senedd/pupil voice groups) to shape school-wide anti-bullying actions. - Provide staff refresher training on identifying and responding to bullying behaviors 2d – Health & Wellbeing - The range of after-school clubs widened to include both traditional sports (e.g. football, netball) and alternative activities (e.g. dance, yoga, fitness). - Pupils given opportunities to represent the school in competitive sporting fixtures/tournaments. - Mid-year review of participation data shows increased pupil involvement in both daily activity and after-school provision. 2e – Pupil Voice - Pupil voice groups demonstrate greater independence in planning, monitoring, and evaluating their own targets. - First Minister and Deputy provide termly feedback to governors on Senedd progress and impact. - Global Gang contributes to a school-wide initiative (e.g. diversity resources, global awareness events). - Pit stops in learning extended beyond immersion days into classroom activities, allowing pupils to reflect and make choices about their learning responses. 2f - Attendance - Weekly: Continue Attendance Cup and celebrate top-attending class in assembly. - Everyday Counts Fortnight: Mid-term challenge — all pupils with 100% attendance over the fortnight entered into a prize draw; winning class earns a treat (e.g. hot chocolate or movie afternoon). - Half Term: Pupils with 100% attendance receive a “Golden Ticket” for a treat (e.g. film afternoon, games). - End of Term: Silver badges awarded for two consecutive terms of 100% attendance. Pupils showing sustained improvement (e.g. moving above 95%) celebrated. Class Incentive: Any class with 96%+ attendance for the term earns a reward afternoon | 2a – Supporting Vulnerable Pupils - Half termly surgeries have been held between ALNCo and class teachers to ensure that provision is in line with the routemap and remains appropriate. - Support plans and pupil progress has been reviewed and provision tailored and tweaked to ensure it remains appropriate to need. - Information regarding pupils on the ALN route map and receiving Wave 1 and Wave 2 provision has been passed on to appropriate staff in readiness for the next academic year. - Dyslexia screening has been repeated with all pupils identified as needing additional support to monitor progress - ELSA training has taken place and additional ELSA support has been planned into the ELSA and Wellbeing timetable. 2b – Outside Agency Support - ALNCo has signposted staff to outreach services for pupils discussed during ALN surgeries where appropriate to do so. 2c - Bullying - Share outcomes of SHRN questionnaire and anti-bullying actions with staff, governors, and parents. - Showcase pupil-led initiatives (e.g. posters, assemblies, pupil ambassadors) to raise awareness of bullying and its impact. - Evaluate the impact of the Voices Against Bullying Programme and workshops, feeding outcomes into the school’s wellbeing priorities. 2d – Health & Wellbeing - Pupil voice survey used to gather feedback on sporting opportunities and suggest new activities. - Inter-class or inter-house competitions introduced to promote regular, inclusive participation. - Sports Day and/or Healthy Schools Week used to showcase progress and celebrate participation. - End-of-year evaluation highlights increased uptake in sports clubs and greater pupil enthusiasm for physical activity. 2e – Pupil Voice - Each pupil voice group produces an end-of-year impact report, sharing outcomes with staff, governors, and pupils. - Senedd demonstrates leadership by influencing a whole-school decision (e.g. policy, curriculum enrichment, or resource allocation). - Global Gang showcases its work in an assembly or event. - Pupil surveys show increased opportunities to make choices in lessons and to influence how learning is structured. 2f - Attendance - Weekly: Ongoing class rewards and celebrations. - Everyday Counts Fortnight: Final challenge of the year — 100% attenders receive entry to a prize draw; class prize could be a picnic, sports afternoon, or ice cream treat. - Half Term: Prize draw for 100% attenders; public recognition for best class attendance. - End of Year: - Gold badges and medals awarded to pupils with 100% attendance for the full year. - Certificates for pupils who have significantly improved attendance across the year. - Winning class with highest annual attendance rewarded with a big treat (e.g. trip, disco, or party). - Family Incentive: Pupils with 100% full-year attendance receive a family prize (e.g. voucher, cinema pass) and recognition at the awards assembly. |

| St Nicholas CIW Primary Development Plan Priorities 2025 - 2026 |  |  |
| --- | --- | --- |
| IA3- Leadership |  |  |
| 1/Engage in high-quality professional development that directly supports pupil progress and school improvement priorities. 2/To continue to develop the role of governors in supporting and challenging the school to secure sustained improvement. 3/ To continue to embed Anti-Racist Practice in Our School |  |  |
| Rationale 3a- CPD Vale of Glamorgan and school mission- Good teaching all of the time without exception Excellence in teaching- Build on existing effective practices, celebrating strengths while introducing innovative strategies to raise teaching quality Teachers in progress step 1 and 2 have been trained in the use of Talk for Writing with high quality training. This now needs to be extended across the school to ensure a consistency of approach. Teachers have used Sue palmer resources however they have expressed the need for guidance on effective writing journeys specific to their progress step or year group. EEF- The local authority as part of the middle tier review have employed the EEF to work with schools to support action research. As a school we have identified that Reading 40% of year 4 to 6 pupils do no maintain or make progress in NRT. This rises to 46% (6 pupils) for our eFSM pupils. 3b- As a school we have worked extensively to develop the role of middle leaders. By continuing to invest in their development, we will strengthen their capacity to lead improvement, support colleagues, and hold peers accountable. 3c- The introduction of the new professional development review began last year. The process needs to embed and be refined. 3d- Our governors have begun working closely with middle leaders, meeting termly to understand key areas for curriculum improvement. Continuing to develop this role will allow governors to deepen their understanding of curriculum planning, implementation, and impact through regular engagement with middle leaders 3e- Our school is committed to creating a community where every child and member of staff feels valued, respected, and represented. To meet the national ambition of the Anti-Racist Wales Action Plan (ARWAP) |  |  |
| Autumn Milestones | Spring Milestones | Summer Milestones |
| . Excellence in teaching - All staff as part of their Professional Development Review have evaluated themselves against the non-pedagogical principles Talk 4 writing/Write path/Welsh writing - Staff receive initial CPD on Pie Corbett’s Talk for Writing principles. - Monitoring of early implementation through learning walks and book scrutiny. - Two CPD session to introduce the principles and structure of The Write Path Cymru. Have been completed - Begin planning and adapting existing writing units to incorporate the approach. - Strategies for using the CSC medium term Welsh planning effectively has been fed back through staff training. - Staff are supported to adapt medium term planning. - Welsh Writing is monitored to ensure coverage and progression. CPD Reading - AOLE (literacy) to carry out a learning walk to establish cpd needs for reading - Deliver initial CPD sessions to all teaching staff on high-quality guided reading strategies - Establish peer observation schedules across progress step 2 and 3 - Teachers trial new strategies for higher order reading approaches 3b AOLE LEADERS - 20 min action plans in place and clearly aligned with whole-school priorities. - TERMLY Monitoring timetable established - PE AND DT snapshots are being used effectively and data analysed 3c- - All staff have agreed professional development review targets aligned to school priorities. - Initial CPD opportunities mapped and accessed. - Baseline evidence of teaching practice gathered (learning walks, lesson observations, pupil voice) 3d - Governors meet with AOLE Leaders to review curriculum areas and identify key areas for improvement for the years - Governors introduced to pupil voice groups and go through action plans 3e - School leads commit to the Equilead professional learning programme. - Initial training sessions attended; school action plan drafted with focus goal - Governors introduced to the - the school’s anti-racist priorities. - Staff continue professional research around becoming Anti-Racist | Excellence in teaching - All staff with the cluster have received practical, motivational training that is directly relevant to their classroom practice. - Staff reflect on practice in teams; early successes shared in staff meetings Talk 4 writing/Write path/Welsh writing - Staff deepen practice of talk for writing approach through ongoing CPD. - team-teaching and sharing of good practice are established to refine talk for writing strategies - Welsh Writing is monitored to ensure coverage and progression. CPD Reading - Provide follow-up CPD and coaching sessions to refine teacher practice in guided reading 3b AOLE LEADERS - 20 min action plans in place and clearly aligned with whole-school priorities. - TERMLY Monitoring timetable established - Maths, Art and Music snapshots are being used effectively and data analysed - Ongoing training has been given to help support effective feedback 3c - Mid-year PDR reviews completed, showing evidence of progress towards targets. - Staff have engaged in at least one peer observation, or collaborative CPD activity. - 3d - Governors participate in termly meetings with AOLE leaders to review progress on curriculum priorities. - Evidence gathered from pupil voice groups is discussed and incorporated into monitoring and challenge. - Minutes show governors actively questioning and supporting curriculum development. 3e - Staff continue to participate in guided professional learning. - Anti-racist principles are visible in curriculum planning, classroom practice, and resource choices. - Reflect on progress of goal and plan second goal - Governors receive an update on progress and provide challenge/support. | Excellence in teaching - All staff demonstrate confident use of multiple evidence-informed teaching strategies. Talk 4 writing /Write path/Welsh writing - Further CPD or T4writing has been given to any staff who still require support - Teachers have implemented 3 full Talk for Writing cycle (imitation → innovation → invention). - Showcase of best practice through staff meeting or INSET; next steps identified for following year in talk for writing - Analyse end-of-year data to evaluate the impact on pupil writing outcomes. - Hold a staff meeting to discuss successes, challenges, and next steps identify opportunities for further professional development and collaboration in non-fiction writing - Writing is monitored to ensure coverage and progression. CPD Reading - Establish a plan for sustaining high-quality guided reading practice for the next academic year. - Reflect on CPD impact and leadership growth; identify next - steps for continued teacher development in reading - 3b AOLE LEADERS - 20 min action plans in place and clearly aligned with whole-school priorities. - TERMLY Monitoring timetable established - All snapshots are being used effectively and data analysed - All AOLE leaders have evaluated their AOLE and fed into SER cycle - 3c - End-of-year PDR reviews demonstrate clear impact of professional development on classroom practice. - Staff reflect on their progress and identify next steps for further growth. 3c - End-of-year review of curriculum priorities with leaders demonstrates progress and improvements. - Governors reflect on their impact and identify areas for continued development in the following year. - Documentation shows measurable improvements in teaching, learning, and pupil outcomes linked to governor involvement. 3e - End-of-year review evidence impact on staff practice, curriculum design, and school culture. - Policies and schemes of work updated to embed anti-racist commitments. - Pupils demonstrate improved understanding of diversity and inclusion through work scrutiny and discussions. - Feedback to Governors. Plan for the following year |

| St Nicholas CIW Primary Development Plan Priorities 2024 - 2025 |  |  |  |
| --- | --- | --- | --- |
| Priority 5: To support pupil and staff wellbeing and continue to implement the new ALN Act. |  |  |  |
| Key actions |  |  |  |
| Rationale |  | Support |  |
| December Milestones | March Milestones |  | July Milestones |
| . |  |  |  |